## VersionControl
Document Name |  | Mfg Scheduling Template | Running Version | V 2.3
Revision Control
Rev No | Rev Date | Revision Reason
0 | 2025-05-02 | Developing the SWE schedule sheet. Identifying and listing activities. Working on Lead Times according to SWE activities/KPI. Discussing on SWE activities to analyse the suitabel KPI and visualizing execution workflow. Working on Layout of SWE Schedule for required information and fields. Discussing on SWE activities to analyse the suitabel KPI and visualizing execution workflow.In depth analysis on workflow in SWE environment and usability approach to link with cross-functional function. Inclusion of other fields to further improve the contents with respect to entry or no-entry of information in the schedule.
2.0 | 2025-05-26 | Version with improvement as user informed observations for functionalities. Integrationr ready to generate automatically from PM.
2.1 | 2025-06-16 | Addition of SWE Comm efforts, Correction of SWE Stage
2.2 | 2025-06-17 | Showing value error at some places in schedule, corrected the same. Installation, Pre-commissioning and Commissioning Lead time linked to PM Editables.
2.3 | 2025-06-23 | Correction of percent update basis on efforts only.

## ReadMe
Document Name |  | Mfg Scheduling Template | Running Version | V 2.3
Guidelines for use
SrNo | Function | Guidelines
1 | SWE | Buffertime is normally to be kept '0'. Required only in rare cases where more time available and some customer milestones need to be synched.
2 | SWE | Mismatch in "Customer Dates" & "PM Dates" is highlighted by red text. This needs to be resolved so that there is no RED, or comment should have clear solution.
3 | SWE | For each applicable efforts on KPI, the applicable non-zero value is to be entered. '0' or ' ' value in efforts column will affect status in dashboard
4 | SWE | LD fields to be filled carefully. There are 4 fields namely, LD Date, LD max/wk, LD max of OV, LD remarks
5 | SWE | The LD max/wk is the max value when multiple LD terms exists based on milestone delivery period
6 | SWE | The warranty terms are to be written in detail as mentioned in PO.
7 | SWE | The scope definition is done at scope area.
8 | SWE | User to enter the actual dates and % completion as per activity completion. The necessary warning & alarms are configured to get wake up call.
9 | SWE | For each stuck KPI, the provision is made to identify the stake holder who can help to progress the KPI. User to select correct from the list. The list contents Engineering (Lite RED) ,Purchase (Orange) ,Software (Lit Blue),Project Management (Blue),Manufacturing (Brown),Sales (Cyan),Client (Purple).
10 | SWE | User can enter suitable remark in the remark column. Essentially, the remark areas is scribble area that can be utilised to generate reminders or list of to do or store historical information for user to refere in later time
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45

## PrjSch
| Guidelines | *OR No. | FSL/2122/DLI/OR001 | [7 empty] | Doc Name & Ver. |  | Trial Release V2.0 | [8 empty] | Start Date |  |  |  |  | Days in SWE |  | LD Date | [61 empty] | Today | [12 empty] | PrjComl% | 99.97%
| Cautions!! | *Master OR | FSL/2122/DLI/OR001 |  | *Sales Engineer |  |  | Girish Sulakshane | [13 empty] | 2021-05-13 |  |  |  |  | 1689 |  | LD max/ wk | [7 empty] | Calender Setting | [6 empty] | Day |  |  |  | Weeklyoff setting1 (Shop) | [8 empty] | Sat | [5 empty] | Schedule Max Date | [7 empty] | 2026-03-30 | [5 empty] | Print, % Completion | [7 empty] | No | [5 empty] | Current Plan | [6 empty] | System Memory Area | [5 empty] | SWDocs | Comm
|  | *WOR No |  |  | *Sales Manager |  |  | Girish Sulakshane | [20 empty] | LD max of OV | [7 empty] | Days | [6 empty] | 1 |  |  |  | Weeklyoff setting2 (Office) | [8 empty] | Sat | [5 empty] | Select Date | [7 empty] | FirstMonth | [19 empty] | Actual Plan | [12 empty] | 99.97% | 0%
| IMS Doc Name | FOX/IA/SALES/019 : Lead Time Chart |  | Ver | V 2.3 | [23 empty] | LD remarks | [13 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [11 empty] | TEfforts | TEfforts
|  |  |  | BFT | Ph | TFO | Phase ID | Task Description | Revised | Plan-1 | Revised | Plan-2 | Revised | Plan-3 | Original | Plan | Ref | Lead Time | Intlk | Effort Days | Current | Plan | Actual | Dates |  |  |  |  | Warranty | 12 months from commissioning or 18 months from the date of dispatch whichever is earlier. | Scope | Scope | Scope | Scope | Scope |  | Sun | Mon | Tue | Wed | Thus | Fri | Sat | Sun | Mon | Tue | Wed | Thus | Fri | Sat | Sun | Mon | Tue | Wed | Thus | Fri | Sat | Sun | Mon | Tue | Wed | Thus | Fri | Sat | Sun | Mon | Tue | Wed | Thus | Fri | Sat | Sun | Mon | Tue | Wed | Thus | Fri | Sat | Sun | Mon | Tue | Wed | Thus | Fri | Sat | Sun | Mon | Tue | Wed | Thus | Fri | Sat | Sun | Mon | Tue | Wed | Thus | [6 empty] | 61 | 0
|  | *Compulsory field | SWE | Buffer Time | Ph | TFO | Phase ID | Task Description | Start Date | End Date | Start Date | End Date | Start Date | End Date | Start Date | End Date | Lead Time |  |  |  | Start Date | End Date | Start Date | End Date | % Complete | Exptd % Complete | Alert Date for 80% | Help required from |  | Remark | HW | SW | MFG | Inst | COM | % Compl | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | [6 empty] | 60.98 | 0
FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL | FL |  | FL | FL | FL | FL | FL | FL | [62 empty] | PMREDActivity | Exptd Compl Days | Act Compl Days | Exptd% | PLREDActivity | Progress Flag |  | BalEfforts | AssignedEfforts | AlertDt Yellow | bar: Sun to Thus
SW |  | *PO Value in lacs | 78.5 |  | P1 | SW | P1-01 | Project Scheduling | [8 empty] | 1 | 1 |  | 0.001 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 100% | 100% | 2021-05-13 |  |  |  | N | N | N | N | N | 100% | [61 empty] | 0 | 0.001 | 0.001 | 100% | 0 | 0 |  |  |  | 0
SW |  | *Customer Name | Eastern Electrolyser Ltd |  | P1 | SW | P1-02 | Internal KOM | [8 empty] | 1 | 1 |  | 0.001 | 2021-05-14 | 2021-05-14 | 2021-05-14 | 2021-05-14 | 100% | 100% | 2021-05-14 | [5 empty] | Scope Details |  |  | 100% | [61 empty] | 0 | 0.001 | 0.001 | 100% | 0 | 0 |  |  |  | 0
SW |  | End Customer | NPCIL Kudankulam Power Project |  | P2 | SW | P2-01 | SW I/P Collection | [8 empty] | 5 | 4 |  | 2 | 2025-11-12 | 2025-11-15 | 2025-11-12 | 2025-11-15 | 100% | 100% | 2025-11-14 09:36 | [8 empty] | 100% | [61 empty] | 0 | 2 | 2 | 100% | 0 | 0 |  | 2 | 2 | 0
SW |  | Consultant | Reliance Infrastructure Ltd. |  | P2 | SW | P2-02 | SW Design Preparation | [8 empty] | 6 | 4 | P1-03 | 2 | 2025-11-16 | 2025-11-19 | 2025-11-16 | 2025-11-19 | 100% | 100% | 2025-11-18 09:36 | [8 empty] | 100% | [61 empty] | 0 | 2 | 2 | 100% | 0 | 0 |  | 2 | 2 | 0
SW |  | *Project Desc. | PLC based control system for Hydrogen BOP packages |  | P2 | SW | P2-03 | SW Design Validation | [8 empty] | 1 | 1 |  | 2 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 100% | 100% | 2025-11-20 | [8 empty] | 100% | [61 empty] | 0 | 2 | 2 | 100% | 0 | 0 |  | 2 | 2 | 0
SW |  | *Section | PLC |  | P2 | SW | P2-04 | SW Documents Submission | [8 empty] | 1 | 1 |  | 1 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 98% | 100% | 2025-11-21 | [8 empty] | 98% | [61 empty] | 1 | 1 | 0.98 | 100% | 1 | 0 |  | 0.98 | 1 | 0
SW |  |  |  |  | P3 | SW | P3-01 | SW Documents Approval | [8 empty] | 8 | 6 |  | 2 | 2025-11-22 | 2025-11-27 | 2025-11-22 | 2025-11-27 | 100% | 100% | 2025-11-26 | [8 empty] | 100% | [61 empty] | 0 | 2 | 2 | 100% | 0 | 0 |  | 2 | 2 | 0
SW | Actual man-days |  | Large |  | P3 | SW | P3-02 | Drive SW | [8 empty] | 63 | 20 |  | 0 | 2025-11-28 | 2025-12-17 | 2025-11-28 | 2025-12-17 | 0% | 0% | 2025-12-13 04:48 | [8 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
SW | 0 | *SW Efforts | 61 |  | P3 | SW | P3-03 | PLC SW | [11 empty] | 30 | 2025-11-28 | 2025-12-17 | 2025-11-28 | 2025-12-17 | 100% | 100% | 2025-12-13 04:48 | [8 empty] | 100% | [61 empty] | 0 | 30 | 30 | 100% | 0 | 0 |  | 30 | 30 | 0
SW |  |  |  |  | P3 | SW | P3-04 | HMI/SCADA | [11 empty] | 12 | 2025-11-28 | 2025-12-17 | 2025-11-28 | 2025-12-17 | 100% | 100% | 2025-12-13 04:48 | [8 empty] | 100% | [61 empty] | 0 | 12 | 12 | 100% | 0 | 0 |  | 12 | 12 | 0
SW |  |  |  |  | P3 | SW | P3-05 | Report | [11 empty] | 2 | 2025-11-28 | 2025-12-17 | 2025-11-28 | 2025-12-17 | 100% | 100% | 2025-12-13 04:48 | [8 empty] | 100% | [61 empty] | 0 | 2 | 2 | 100% | 0 | 0 |  | 2 | 2 | 0
SW |  |  |  |  | P3 | SW | P3-06 | Internal testing | [11 empty] | 2 | 2025-11-28 | 2025-12-17 | 2025-11-28 | 2025-12-17 | 100% | 100% | 2025-12-13 04:48 | [8 empty] | 100% | [61 empty] | 0 | 2 | 2 | 100% | 0 | 0 |  | 2 | 2 | 0
SW |  |  |  |  | P3 | SW | P3-07 | SW FAT Call with Test Report | [8 empty] | 4 | 4 |  | 1 | 2025-12-18 | 2025-12-21 | 2025-12-18 | 2025-12-21 | 100% | 100% | 2025-12-20 09:36 | [8 empty] | 100% | [61 empty] | 0 | 1 | 1 | 100% | 0 | 0 |  | 1 | 1 | 0
SW |  |  |  |  | P3 | SW | P3-08 | SW FAT | [8 empty] | 2 | 2 |  | 3 | 2025-12-22 | 2025-12-23 | 2025-12-22 | 2025-12-23 | 100% | 100% | 2025-12-22 19:12 | [8 empty] | 100% | [61 empty] | 0 | 3 | 3 | 100% | 0 | 0 |  | 3 | 3 | 0
SW |  |  |  |  | P3 | SW | P3-09 | SW FAT Compliance | [8 empty] | 2 | 2 |  | 2 | 2025-12-24 | 2025-12-25 | 2025-12-24 | 2025-12-25 | 100% | 100% | 2025-12-24 19:12 | [8 empty] | 100% | [61 empty] | 0 | 2 | 2 | 100% | 0 | 0 |  | 2 | 2 | 0
EC |  |  |  |  | P4 | EC | P4-01 | Installation | [8 empty] | 0 | 0 |  | 0 |  |  |  |  | 0% | 0% | [9 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
EC |  |  |  |  | P4 | EC | P4-02 | Pre-Commissioning | [8 empty] | 0 | 0 |  | 0 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 0% | 0% | 2026-03-02 | [8 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
EC |  |  |  |  | P5 | EC | P5-01 | Commissioning | [8 empty] | 0 | 0 |  | 0 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 0% | 0% | 2026-03-30 | [8 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
EC |  | PM Dates | SWE Dates |  | P5 | EC | P5-02 | Final MOM/Site Report | [8 empty] | 0 | 0 |  | 0 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 0% | 0% | 2026-03-30 | [8 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
SW | Internal KOM | 2021-05-14 | 2021-05-14 |  | P5 | SW | P5-03 | As Comm. Doc (SW) | [8 empty] | 8 | 0 |  | 0.001 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 0% | 0% | 2026-03-30 | [8 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  |  |  | 0
EC | SW Input | 2025-11-12 | 2025-11-12 |  | P5 | EC | P5-04 | Post Comm. Support | [8 empty] | 0 | 0 |  | 0 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 0% | 0% | 2026-03-30 | [8 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 | 0 | 0
SW | SW FAT | 2025-12-22 | 2025-12-22 |  | P5 | SW | P5-05 | Project Closure | [8 empty] | 0 | 0 |  | 0.001 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 0% | 0% | 2026-03-30 | [8 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  |  |  | 0
| Install | [34 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
| PreComm. | 2026-03-02 | 2026-03-02 | [32 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
| Comm. | 2026-03-30 | 2026-03-30 | [32 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
[36 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
| Stake Holders | [34 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
| Sales | UM | [33 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
| PM | NSK | [33 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
| HW | KSP | [33 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
| BYR | RVL | [33 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
| MFG | SBP | [33 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
| SW | CP | [33 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
| E&C | CP | [33 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
| A/C | GER | [33 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
[36 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
[36 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
[36 empty] | 0% | [61 empty] | 0 | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0
[36 empty] | 0% | [70 empty] | 0
[36 empty] | 0% | [70 empty] | 0
[36 empty] | 0% | [70 empty] | 0
[36 empty] | 0% | [70 empty] | 0
[36 empty] | 0% | [70 empty] | 0
[36 empty] | 0% | [70 empty] | 0
[36 empty] | 0% | [70 empty] | 0
[36 empty] | 0% | [70 empty] | 0
|  | Schedule File Name | [33 empty] | 0% | [70 empty] | 0
SWESch_FSL_2122_DLI_OR001_PLC.xlsx
Formulas:
FL = IFERROR(IF([FL]>0,[FL]-[FL]+1,[FL]),"")
FL = IFERROR(IF([FL]>0,[FL, row below]-1,[FL, row below]),"")
PMREDActivity = IF(OR(AND(TODAY()>[FL],[FL]<>1,[Exptd%]=1),AND([Exptd%]>='@LeadT_Setting'!$AK6,[FL]<='@LeadT_Setting'!$AK6),AND([FL]<([Exptd%]-'@LeadT_Setting'!$AI6),[Exptd%]>[FL],[FL]>0,[Exptd%]<'@LeadT_Setting'!$AK6)),1,0)
Exptd% = IFERROR(IF(OR([FL]<=0,TODAY()<[FL]),0,IF(TODAY()>=[FL],1,((TODAY()-[FL]))/(([FL]-[FL])))),0)
PLREDActivity = IF(OR(AND(TODAY()>[FL],[FL]<>1,[Exptd%]=1),AND([Exptd%]>='@LeadT_Setting'!$AK6,[FL]<='@LeadT_Setting'!$AK6),AND([FL]<([Exptd%]-'@LeadT_Setting'!$AJ6),[Exptd%]>[FL],[FL]>0)),1,0)
AlertDt Yellow = IF(OR(AND([FL]>0,TODAY()>=[FL],[FL]<80%,NOT(ISBLANK([FL]))),AND([FL]<>1,[FL]>0,[FL]<TODAY(),ISBLANK([FL]))),1,0)
Note on C1: Sales Order number
Note on AB1: Actual Panel Dispatch End Date -Actual Panel Manufacturing Start Date+1
Note on C2: Master Sales Order number.
Note on C3: Master Sales Order number.
Note on F6: Project Phase
Note on G6: Task Function Owner
Note on F7: Project Phase
Note on G7: Task Function Owner
Note on V11: Indicates with RED background if this date is smaller than the Internal KOM date
Note on D17: (sizing in Days) Small : 1 to 14 Medium : 15 to 60 Large : 61 to 100 Very Large : 101 to 150 Non-Standard : 151 & above

## AmendmentIndex (hidden)
Amendment Index
|  | Sales OR | FSL/2122/DLI/OR001
|  | Section | PLC based control system for Hydrogen BOP packages
|  | Customer Name | 78.5
0
| Dwg No | Rev | Amendment Description | Mfg Efforts Description | Hours | Date Raised | Date Closed
EndRow | EndRow | EndRow | EndRow | EndRow | EndRow | EndRow | EndRow | EndRow

## @LeadT_Setting (hidden)
[5 empty] | Small | Medium | Large | Very Large | Non-Standard |  |  |  |  | Days | HW | 4 | 10 | 50 | 75 | Very Large
|  |  | In | Clearance to Mfg | 1.4286 | 2.4286 | 3.1429 | 4.5714 | 9.4286 |  | 1.6807 |  |  | No. | MFG | 5 | 15 | 25 | 50 | Non-Standard | 0
|  |  | Weeks | Clearance to Dispatch | 0.28571 | 0.85714 | 1.5714 | 2.1429 | 5.2857 |  |  |  |  | Days | SW | 14 | 60 | 100 | 150 | Large
Sec. | Ph | TFO | Phase ID | Task Description | Ref Lead Time | Ref Lead Time | Ref Lead Time | Ref Lead Time | Ref Lead Time |  | PM | SW | HW |  |  | Medium | Large | Vlarge | Non-Standard | [39 empty] | Delay Reason | Delay Code
FL | FL | FL | FL | FL | FL | FL | FL | FL | FL |  | Schedule | [8 empty] | PM Alarm | PL Alarm | Default Alarm % | Payment Status | Mfg LOC | Warranty | Warranty Meaning | [32 empty] | FL | FL
| P1 | SW | P1-01 | Project Scheduling | 0 | 1 | 1 | 2 | 8 | Supervisor | Run | [8 empty] | 20% | 10% | 80% |  |  | Standard | 24 months from the date of commissioning or 30 months from the date of supply, whichever is earlier. Faulty material to be delivered at our premises and replacement to be collected from our premises. | [31 empty] | Legend | Mfg Manpower shortage | D001
| P1 | SW | P1-02 | Internal KOM | 0 | 1 | 1 | 2 | 16 | Supervisor | Hold | [11 empty] | Received | GON | [33 empty] | Dxxx : Delay | Mfg Manpower engaged | D002
| P1 | SW | P1-03 | SW I/P Collection | 3 | 4 | 5 | 7 | 15 | Fitter | Closed | [12 empty] | DUB | [6 empty] | SW | SW | SW | SW | SW | SW | SW | SW | SW | SW | SW | SW | SW | SW | SW | EC | EC | EC | EC | SW | EC | SW | [5 empty] | Exxx: Error | Sales Material available <85% | S001
| P2 | SW | P2-01 | SW Design Preparation | 2 | 4 | 6 | 8 | 12 | Electrician | [20 empty] | Project Scheduling | Internal KOM | SW I/P Collection | SW Design Preparation | SW Design Validation | SW Documents Submission | SW Documents Approval | Drive SW | PLC SW | HMI/SCADA | Report | Internal testing | SW FAT Call with Test Report | SW FAT | SW FAT Compliance | Installation | Pre-Commissioning | Commissioning | Final MOM/Site Report | As Comm. Doc (SW) | Post Comm. Support | Project Closure | Engg | RED | 1 | Engineering | Engineering,Purchase,Software,Project Management,Manufacturing | Sxxx: Supply chain | Sales main material shortfall | S002
| P2 | SW | P2-02 | SW Design Validation | 1 | 1 | 1 | 3 | 5 | Electrician | [13 empty] | 0 | #N/A |  | SrNo | SWE Status | SWDocs | 0 | [22 empty] | Pur/Buyr | ORANGE | 2 | Purchase |  |  | Vendor sent wrong material | S003
| P2 | SW | P2-03 | SW Documents Submission | 1 | 1 | 1 | 3 | 8 | Electrician | [10 empty] | HW Efforts | SW Efforts | No of Panels | Panel Packaging Type | Lead Time |  | 1 | Init | Init | 1 |  | 1 | [20 empty] | Softw | LitBLUE | 3 | Software |  |  | Material Quality cocnern | S004
| P3 | SW | P3-01 | SW Documents Approval | 4 | 6 | 8 | 10 | 10 | Engineer | [9 empty] | Small | 1,4 | 1,14 | 1,5 | Client's Scope | 0 |  | 2 | SWInput | SWInput | 1 |  |  | 1 | [19 empty] | PM | BLUE | 4 | Project Management |  |  | Wrong Material ordered | E001
| P3 | SW | P3-02 | Drive SW | 21 | 35 | 63 | 75 | 90 | Engineer | [9 empty] | Medium | 5,10 | 15,60 | 6,15 | Domestic Crate Econo | 1 |  | 3 | Design | Design | 1 |  |  |  | 1 | 1 | [17 empty] | Mfg | BROWN | 5 | Manufacturing |  |  | Short of material ordering | E002
| P3 | SW | P3-03 | PLC SW | [5 empty] | Supervisor | [9 empty] | Large | 11,50 | 61,100 | 16,25 | Domestic Crate Std | 1 |  | 4 | SWDocs | SWDocs | 0 | [5 empty] | 0.98 | [16 empty] | Sales | CYAN | 6 | Sales |  |  | WD corrections | E003
| P3 | SW | P3-04 | HMI/SCADA | [5 empty] | Engineer | [9 empty] | Very Large | 51,75 | 101,150 | 26,50 | Domestic Box Wood | 1 |  | 5 | SWDocsAprv | SWDocsAprv | 1 | [6 empty] | 1 | [15 empty] | Client | PURPLE | 7 | Client |  |  | Project Priority changed | D003
| P3 | SW | P3-05 | Report | [5 empty] | Engineer | [9 empty] | Non-Standard | 76 | 151 | 51 | Domestic Box Ply+Wood | 2 |  | 6 | DriveSW | DriveSW | 0 | [7 empty] | 0 | [20 empty] | WD changed | D004
| P3 | SW | P3-06 | Internal testing | [5 empty] | Supervisor | [13 empty] | Domestic Base Econo | 2 |  | 7 | PLCSW | PLCSW | 1 | [8 empty] | 1 | [19 empty] | Mechanical rework | D005
| P3 | SW | P3-07 | SW FAT Call with Test Report | 4 | 5 | 4 | 4 | 4 | Fitter | [13 empty] | Export Crate Econo | 2 |  | 8 | SCADA | SCADA | 1 | [9 empty] | 1 | [18 empty] | Electrical rework | D006
| P3 | SW | P3-08 | SW FAT | 2 | 2 | 2 | 6 | 8 | Supervisor | [13 empty] | Export Box Std | 3 |  | 9 | Report | Report | 1 | [10 empty] | 1 | [17 empty] | Configuration rework | D007
| P4 | SW | P4-01 | SW FAT Compliance | 2 | 2 | 2 | 4 | 4 | Engineer | [13 empty] | Export Box Seaworthy | 4 |  | 10 | InternalTest | InternalTest | 1 | [11 empty] | 1 | [16 empty] | PLC/HMI program concerns | D008
| P4 | EC | P4-02 | Installation | 0 | 0 | 0 | 0 | 0 | Supervisor | [16 empty] | 11 | SWFAT | SWFAT | 1 | [12 empty] | 1 | 1 | 1 | [13 empty] | Drive program concerns | D009
| P4 | EC | P4-03 | Pre-Commissioning | 0 | 0 | 0 | 0 | 0 | Supervisor | [15 empty] | Stored | 12 | Installation | Installation | 0 | [15 empty] | 0 | [12 empty] | Product limitation | D010
| P5 | EC | P5-01 | Commissioning | 0 | 0 | 0 | 0 | 0 | Supervisor | [15 empty] | Hold | 13 | PreComm | PreComm | 0 | [16 empty] | 0 | [11 empty] | Damaged Material | S005
| P5 | EC | P5-02 | Final MOM/Site Report | 0 | 0 | 0 | 0 | 0 | Supervisor | [15 empty] | Cancelled | 14 | Comm | Comm | 0 | [17 empty] | 0 | 0 | [9 empty] | Wrong drilling/tapping | E004
| P5 | SW | P5-03 | As Comm. Doc (SW) | 2 | 4 | 8 | 10 | 12 | Fitter | [15 empty] | Closed | 15 | As-CommDoc | As-CommDoc | 0 | [19 empty] | 0 | [8 empty] | Wrong cutout | E005
| P5 | EC | P5-03 | Post Comm. Support | 0 | 0 | 1 | 0 | 0 | Engineer | [16 empty] | 16 | PostCommSup | PostCommSup | 0 | [20 empty] | 0 | [7 empty] | Dispatch Delayed | D011
| P5 | SW | P5-03 | Project Closure | 0 | 0 | 0 | 1 | 1 | Supervisor | [16 empty] | 17 | Closed | Closed | 0 | [21 empty] | 0 | [6 empty] | Third party inspection | D012
[10 empty] | Supervisor | [16 empty] | 18 | [31 empty] | Extended iFAT | D013
[10 empty] | Fitter | [48 empty] | Extended cFAT | D014
Supervisor
Supervisor
90
60
1.5
Critical Material Lead time
Normal Material Lead time
Note on AD7: Sales + HW + SW + SP + AC + MF
Note on AD23: If you have very less time for dispatch then order Packing Material